## original
Project Name:
Project Manager:
Start Date:
Task | Resource | Duration (days) | Rate/day | Direct Labour Cost
Analysis of Cost Planning | C1 | 20 | 1600 | 32000
| C2 | 20 | 1600 | 32000
Detailed Analysis of the Effectiveness of Project Planning | C1 | 5 | 1600 | 8000
| C2 | 0
Improvement of Project Planning Processes | C1 | 10 | 1600 | 16000
| C2 | 15 | 1600 | 24000
Detailed Description of Project Planning Metrics | C1 | 20 | 1600 | 32000
Selection of Project Planning Software | C1 | 30 | 1600 | 48000
| C2 | 20 | 1600 | 32000
Meeting with Supplier | C1 | 0 | 1600 | 0
| C2 | 10 | 1600 | 16000
Discussion of Report with MD | C1 | 1 | 1600 | 1600
Writing of Final PMO Report | C2 | 10 | 1600 | 16000
Presentation of Final PMO Report | C1 | 1 | 1600 | 1600
259200
OTHER LABOUR COST
S1 |  |  | 13000
S2 |  |  | 13000
SPO |  |  | 21000
47000
TOTAL LABOUR COST |  |  |  | 306200
OVERHEADS
Accomodation |  |  | 11700
Travel |  |  | 16000
Meetings |  |  | 25000
52700
FIXED COST
PC hardware |  |  | 15000
Software |  |  | 25000
Miscellaneous |  |  | 8000
48000
Training Cost |  |  |  | 50000
Cost Estimate |  |  |  | 763100
Contingency 10% |  |  |  | 76310
Baseline Cost |  |  |  | 839410
Management Reserve |  |  |  | 10590
Project Budget |  |  |  | 850000