## original
Project Name:
Project Manager:
Client:
Start Date:
DIRECT LABOUR COST | Total Effort (hrs) | Rate/hr | Cost
Sprint 1
Analysis of Cost Planning | 20 | 200 | 4000
Detailed Analysis of the Effectiveness of Project Planning | 5 | 200 | 1000
Sprint 2 |  |  | 0
Improvement of Project Planning Processes | 10 | 200 | 2000
Detailed Description of Project Planning Metrics | 20 | 200 | 4000
Sprint 3 |  |  | 0
Selection of Project Planning Software | 30 | 200 | 6000
Meeting with Supplier | 10 | 200 | 2000
Sprint 4 |  |  | 0
Discussion of Report with MD | 1 | 200 | 200
Writing of Final PMO Report | 10 | 200 | 2000
Presentation of Final PMO Report | 1 | 200 | 200
TOTAL DIRECT LABOUR COST |  |  | 21400
DIRECT VARIABLE COST | Units | Rate | Cost
Accomodations (no of weeks) | 20 | 400 | 8000
Meetings (no of meetings held) | 5 | 500 | 2500
TOTAL DIRECT VARIABLE COST |  |  | 10500
DIRECT FIXED COST
Hardware |  |  | 15000
Software |  |  | 25000
Training |  |  | 10000
8000
TOTAL DIRECT FIXED COST |  |  | 58000
Cost Estimate |  |  | 89900
Contingency 10% |  |  | 8990
Baseline Cost |  |  | 98890
Profit |  |  | 51110
PROJECT BUDGET |  |  | 150000