## Slide 1: Session 3.2: Project Methodology and Project Start Up
Dr Andre Samuel
andre.samuel@sam.edu.tt

## Slide 2
Learning Outcomes

## Slide 3: Recap Session 3.1

## Slide 4: PM Interpersonal Skills PMI (2021)
Leadership
Team building
Motivation
Communication
Influencing
Decision making
Political and cultural awareness
Negotiation
Trust building
Conflict management
Coaching

## Slide 5: What Are Power Skills?
PMI (2022) defines power skills as abilities and behaviors that facilitate working with others and help project professionals to succeed in the workplace.
Some individuals and other organizations also refer to them as “soft skills” or “interpersonal skills.”
PMI 2022

## Slide 6: For Part 1.b- Reflection before and after module
You can adapt and use the template
Project Management Skills | Did you have this skill (before the module)? Yes No | If YES score 1 - 5 (with 1 being less skilled and 5 being most skilled) How can you evidence this skill? | Did you improve in this skill by the end of the module? | End of module score 1 - 5 (with 1 being less skilled and 5 being most skilled)

## Slide 7: Stages of Team development
Tuckman (1965) says that teams go through 4 phases: forming; storming; norming and performing. He added adjourning later in 1975.
It is important to be aware of these phases in your project and manage them effectively – project progress depends on it
1
Forming
2
Storming
4
Performing
3
Norming

## Slide 8: Project Governance and Internal Project Team (adapted from Maylor, 2017, pp. 62)
 | PROJECT BOARD/PROJECT STEERING GROUP | 
USER REPRESENTATIVE | PROJECT SPONSOR | SUPPLIER REPRESENTATIVE
Senior User | Executive/Senior responsible Owner | Senior Supplier
CHANGE BOARD Delegated authority Technical capability
PROJECT MANAGEMENT OFFICE Admin support Technical support Configuration management
PROJECT MANAGER
TEAM MANAGER
TEAM MANAGER
TEAM MEMBERS
TEAM MEMBERS
PROGRAMME MANAGEMENT
TECHNICAL ADVISORY GROUP
Notes: As a Project Manager you are working within the organisational structure. You will need to work with the governance in place, e.g. the Project Board/Steering Group and also need to lead your project team

## Slide 9: Belbin Team Roles
Types of Roles | Roles | Key features
Action Oriented Roles | Shaper Implementer Completer/Finisher | Challenges the team to improve Puts ideas into action Ensures thorough, timely completion
People Oriented Roles | Coordinator Team Worker Resource Investigator | Acts as chairperson Encourages cooperation Explores outside opportunities
Thought Oriented Roles | Plant Monitor-Evaluator Specialist | Presents new ideas and approaches Analyzes the options Provides specialized skill
What was the outcome of the Belbin Team Roles Questionnaire?

## Slide 10: Project Methodology and Lifecyles

## Slide 11: Why do we need a Project Methodology?
Concepts and Structure
Common methods and rules
Standardize Delivery
Provide a Framework for management
Procedure and steps
“There’s method to his madness”
Shakespeare-Hamlet

## Slide 12: Activity- Why use a Project Methodology?
Ready-
  “If you DO NOT use a methodology, what would be the results?
  Think of ONE WORD
  Post in the Chat

## Slide 13: Pulse of the Profession by PMI

## Slide 14: Why do we need a project methodology?
APM’s (2015) Project success research discovered 5 most key factors that make projects successful.
3 of them relate to project management method:
  Project planning and review
  Goals and objectives
  Effective governance
The other 2 relate to skills and commitment
Notes: Full list of 12:
1. Project planning and review
Pre-project planning should be thorough and considered, with monitoring and review throughout the project.
2. Goals and objectives
The overall goal of the project should be clearly specified and recognised by all stakeholders involved in the project.
3. Effective governance
The project needs to have clear reporting lines and regular communications between all parties.
4. Competent project teams
The project professionals leading, or forming a core team, need to be fully competent.
5. Commitment to success
All parties involved in the project must be, and remain, committed to the project’s success.
Capable sponsors Sponsors play an active role in the life cycle of the project; they assume ultimate responsibility and accountability for the project outcomes.5 Secure funding The project has a secure funding base; contingency funding is recognised from the start and tight control of budgets is in place to ensure maximum value is realised.
Supportive organisations The environment in which the project operates is project-friendly; the organisation provides support and resourcing for project activity (including financing) and access to stakeholders.
End users and operators End users or operators are engaged in the design of the project; the project team engages with users, who are able to take on what the project has produced effectively and efficiently.
Aligned supply chain All direct and indirect suppliers are aware of project needs, schedules and quality standards. Higher and lower tiers of supply chains are coordinated.
Proven methods and tools Good practice project management tools, methods and techniques are applied in a way which maintains an effective balance between flexibility and robustness.
Appropriate standards Quality standards are actively used to drive quality of outputs. Adherence to other standards is regularly monitored in order to ensure delivery is to best practice levels

## Slide 15: Waterfall method (Royce, 1970)
Some with roots in information technology development, e.g.
Waterfall method (originally for software developed by Royce (1970)
Requirements
Design
Implementation
Verification
Maintenance
Notes: Royce’s original stages: System requirements, Software Requirements, Analysis, Program Design, Coding, Testing, Operations

## Slide 16: Waterfall- Linear methods have been criticised
Too slow, not dynamic
Not all requirements known at the beginning
Too rigid
Need to adapt to change
Indeed in software development, Rapid Applications Development (prototyping) was adopted.
Agile Project Management took over.
  SCRUM is one particular development of agile project management

## Slide 17: Agile Project Management
Agile project management is an approach based on:
  delivering requirements iteratively and
  incrementally throughout the project life cycle.
At the core of agile is the requirement to exhibit central values and behaviours of
  trust
  Flexibility
  empowerment and collaboration.

## Slide 18: Why Agile?

## Slide 19: Characteristics of Agile
Agile starts work with a rough idea and as the project progresses clarifies the requirements
Delivers work in short bursts (or sprints) of anything up to a few weeks.
These are repeated to refine the working deliverable until it meets the client's requirements.
Collaborative relationships are established between stakeholders and the team members delivering the work
Sprint 1
Sprint 2
Sprint 3
Product Burndown

## Slide 20: Activity- Agile Word Cloud
When you hear the term “Agile Methodology”, what words come to mind?
Go to: https://www.menti.com/d7r32t81pe
Give 3 words that come to mind

## Slide 21
Agile projects need documentation, reviews and processes just as traditional projects do to meet requirements, manage costs and schedules, deliver benefits and avoid scope creep;
Agile does not expect to fully understand the requirements before work can begin.
Instead it emphasises the importance of delivering a working product as something tangible for the client that can then be refined until it fulfils the client's needs.
The key measure of project progress is this series of working deliverables.

## Slide 22: Principles of Agile
Customer collaboration over contract negotiation
Individuals and interaction over processes and tools
Responding to change over following a structured plan
Prototyping/working solutions over comprehensive documentation

## Slide 23: Agile Benefits
Reduce Waste
Focus on Customer Needs
Faster detection of Issues
Increased Flexibility
Agile Benefits To Project Management
Increased Adaptability
Faster Turnaround

## Slide 24: Implication of Agile to Project Management
Project Management Function | Implication
Planning | Less formal, based on sprints
Scope | Collaborative and interactive approach to requirements as they are not fully known. Change is welcomed, scope creep is expected
Cost | Based on number of sprints and effort, iterative, bottom up
Quality | Early testing, continuous improvement
Project Team | Greater communication and collaboration

## Slide 25: Agile Methodologies
Scrum
Lean
Kanban
DSDM

## Slide 26: PMI (2017) 5 Process Groups and Maylor’s (2017) 4Ds
In this module, we will mainly draw from PMI’s (2017) and Maylor’s (2017 methodologies:
Project Start Up/Initiation – similar to D1 Define it
Planning – similar to D2 Design it
Executing/Managing Deployment – similar to D3 Do it
Monitoring and controlling in D3 Do it and Define it
Project Close/Closing – similar to D4 Develop it
Planning
Processes
Executing
Processes
Initiating Processes
Closing
Processes
Monitoring &
Controlling Processes
PMI’s (2017) 5 Process Groups
D1:
Define it!
D2:
Design it!
D3:
Do it!
D4:
Develop it!
The brief
The proposal/PID
The outcomes
Process and product knowledge
Maylor’s (2017) 4 D’s Product Lifecycle

## Slide 27: Project Lifecycle
This is in linear format – but projects can be iterative or agile. Presented in linear format for clarity.
Project Start Up
Integrated Planning
Managing Deployment
Monitoring and Controlling Processes
Project Close
Why/what is the project
Project charter
Objectives
Team structure
Risks
Stakeholders
Scope
Budget/Costs
Work Breakdown Structure
Gantt chart
Communication plan
Risk management
Direct/manage
Quality management
Team management
Communications
Stakeholders
Lessons learnt
Reporting
Status/tracking
Project control
Scope, Cost, Schedule Quality and Resources Control
Risk monitoring

## Slide 28: Let’s apply these stages…
How would you set up new restaurant?....
Project Start Up
Integrated Planning
Managing Deployment
Monitoring and Controlling Processes
Project Close
What shall be the concept of the restaurant?:
Objectives?
Who needs to be in the team?
What are the risks?
Who are the stakeholders? (people/organisations impacted by and who have an impact on the project)
What work is there to do?
Produce:
Gantt chart
Communication plan
Risk management
What needs to be managed as the project runs?
How can we close this project?
What shall we monitor as the restaurant is set up?

## Slide 29: Possible example summary of the set-up new restaurant project
Set up new restaurant
Initiating Processes
Planning Processes
Executing Processes
Monitoring and Controlling Processes
Closing Processes
Concept: Healthy but delicious!
Deliver a healthy and tasty menu for target customers
Team structure:
    Chef
    Serving staff
    Marketing
    Etc.
Risks
Stakeholders
    Potential customers
    Food hygiene
    Community
    Funders
    Planning
    Etc.
WBS:
  Design the menu
  Kitchen design and layout
  Restaurant design and layout
  Purchasing of equipment and furniture
  Installation and decoration
  Training staff
  Launch, publicity etc.
Gantt chart
Communication plan
Risk management
Direct/manage:
    Ensure the kitchen is developed on time
    Manage the design and setting up of restaurant
    Work on the communications and marketing
Quality management
    Recipe design and testing
    Design of layout, furniture to met customers’ impression.
Team management
Communications
Stakeholders
Launch event – celebrate the work of the project team
Lessons learnt
Reporting
  To funders
  To planning
Status/tracking
  On time for launch
  All processes working together
Project control
Scope, Cost, Schedule, Quality and Resources Control
Risk monitoring

## Slide 30: Summary
Different methodologies for project management.
Need some flexibility to incorporate change and respond
Define PMI’s (2017) 5 process groups: start up/initiating, planning, deployment/executing, monitoring and controlling and closing.
Begin to understand the management activities in each of these process groups (we will build further on this over the rest of the module)

## Slide 31: BREAK
Take a 10 minute break, after the break…

## Slide 32: Project Start Up
Setting Project Objectives
Stakeholder Management
Identifying Risks
Project Charter

## Slide 33: Project Start Up
Why/what is the project?
Project can be anything and any size
Internal or external customer based projects
Important in this stage…
Project specification and requirements
  Better the specification, better the project outcome
  Timing and deliverables
Identification of stakeholders
Overall project risk
Integrated Planning
Managing Deployment
Project Start Up
Project Close
Monitoring &
Controlling Processes
Main output: Project Charter

## Slide 34: Setting Project Objectives

## Slide 35: Project specification: Objectives
The overall goal of the project should be clearly specified and recognised by all stakeholders involved in the project
An objective is:
  a statement of results to be achieved
  time based
  with conditions specified
SPECIFIC
MEASURABLE
ACTIVITY and ACHIEVEMENT BASED
REALISTIC and RELEVANT
TIMED
Scope
Cost
Time
Quality

## Slide 36: Consider the example of “Setting up a restaurant”
 Set up restaurant
Is this a SMART objective?
SPECIFIC
MEASURABLE
ACTIVITY and ACHIEVEMENT BASED
REALISTIC and RELEVANT
TIMED
Break the idea down into SMART objectives, for example:
Design a restaurant interior that conveys comfort and health by 18 June in line with a budget of £820,000
Develop marketing assets: logo, branding, tagline and visuals by
2 July
conveys comfort and health
restaurant interior that
specific
£820,000
budget of
measurable
Design
activity
18 June
timed
branding, tagline and visuals
marketing assets: logo,
specific
measurable
Develop
activity
2 July
timed
Notes: Break the idea down into SMART objectives, for example:
Design a restaurant interior that conveys comfort and health by 18 June in line with a budget of £820,000
Design a kitchen that is ergonomic with an efficient layout to prepare healthy meals by 18 June in line with a budget of £450,000
Purchase all required kitchen and restaurant fixtures and fittings to begin construction and installation on 18 June, with a total budget of £1,270,000
Oversee the installation of the kitchen and restaurant to a high standard with a completion date of 30 July.
Conduct market research into the tastes and customer preferences in the area by 11 June.
Develop recipes that are delicious and designed with good nutrition using the recommended daily nutritional values by 2 July
Establish supplier relationships with key suppliers by 16 July
Test recipes with customers and consider feedback by 23 July
Final menu confirmed by 30 July
Develop marketing assets: logo, branding, tagline and visuals by 2 July
Prepare and market launch event by 9 July
Launch restaurant on 6th August

## Slide 37: Activity: Write an objective for and analyse it.
Imagine you had been tasked with organising a “Welcome Back!” event for your course for after the summer vacation in Sept, 2024.
Write one objective for this Project
Post in the Chat
SPECIFIC
MEASURABLE
ACTIVITY and ACHIEVEMENT BASED
REALISTIC and RELEVANT
TIMED

## Slide 38: Project Requirements
Definitions
Requirements – “A condition or capability that is required to be present in a product, service or result to satisfy a business need.”
PMI, 2021, pp. 247
Requirements Management Plan – “A component of the project or program management plan that describes how requirements will be analysed, documented and managed.
PMI, 2021, pp. 247
?
?
?
?
?
?
?
What?

## Slide 39: Maylor (2017) links together stakeholders, requirements and measures (pp. 76)
Item | Definition | Examples
Stakeholders | Any individual or group with an interest in the project outcome. | The project customers, the delivery team, the end beneficiaries of the project, anyone affected by the outcome, proponents and opponents of any change
Requirements | What each individual or group wants from the process or outcome | Defined requirements in the form of a specification or contract, implicit requirements (I want this project to be a good place to work), or legal/ethical/moral/commercial. Competitive requirements
Measures | The means by which it will be determined during and post project whether those requirements have been met | Level of compliance to the specification, customer satisfaction, level of return on investment, staff retention levels
Stakeholders

## Slide 40: How do we collect requirements?
Collect data from project team and stakeholders:
  Brainstorming
  Interviews (with stakeholders)
  Focus Groups (interactive discussion with key stakeholders and subject matter experts)
  Questionnaires and surveys (pre-designed questions – can ask lots of people and get statistical data)
  Benchmarking
Stakeholders
Team &
Organisation

## Slide 41: Requirements Traceability Matrix
A table that links requirements to their origin and traces them throughout the project lifecycle.
ID | Associate ID | Requirements Description | Business Needs, Opportunities, Goals, Objectives | Project Objectives | WBS Deliverables | Product Design | Product Development | Test Cases

## Slide 42: Stakeholder Management

## Slide 43: Stakeholder Management
Stakeholders are people, groups or organisations that could impact or be impacted by the project
Identify stakeholder groups and analyse their power and interest
Stakeholders

## Slide 44: Stakeholder Groups and the Environment
Rest of the world
Core externals
Internal team
Adapted from Figure 4.1 (Maylor, 2017, pp.78)
Inputs
Project
Out-comes
Constraints
Require-ments
Stakeholders

## Slide 45: Internal Stakeholders Project Team (adapted from Maylor, 2017, pp. 62)
 | PROJECT BOARD/PROJECT STEERING GROUP | 
USER REPRESENTATIVE | PROJECT SPONSOR | SUPPLIER REPRESENTATIVE
Senior User | Executive/Senior responsible Owner | Senior Supplier
CHANGE BOARD Delegated authority Technical capability
PROJECT MANAGEMENT OFFICE Admin support Technical support Configuration management
PROJECT MANAGER
TEAM MANAGER
TEAM MANAGER
TEAM MEMBERS
TEAM MEMBERS
PROGRAMME MANAGEMENT
TECHNICAL ADVISORY GROUP

## Slide 46: Restaurant Example: Who are the stakeholders?
Rest of the world
Core externals
Internal team
Adapted from Figure 4.1 (Maylor, 2017, pp.78)

## Slide 47: Restaurant Example: Stakeholder Groups
Rest of the world
Core externals
Internal team
Marketing Consultant
Marketing intern
Procurement Administrator
Project Administrator
Building contractor
Electrical contractor
Heating contractor
Suppliers
Sponsor
Competitors
Customers
Food Standards Agency
Council planning
Existing restaurants in the group
Building control
Food critics
Local press
Review websites
Social media outlets

## Slide 48: Power/Interest Grid
Low
High
Interest
Low
High
Power
Keep satisfied
Moderate priority group
Need to keep this group sufficiently involved
Key Player and Manage expectations
Highest priority for the project manager
Manage actively through active engagement
Monitor only
Lowest level for the project manager
Don’t overload them with communication
Keep informed
Moderate priority group
Objective is to sustain their interest and leverage when useful to the project
Stakeholder mapping
Stakeholders

## Slide 49: Example from Maylor (2017), pp. 92
European Transport Infrastructure

## Slide 50: Group Activity- Analyse Stakeholders
Using the Restaurant Project
Identify:
  Choose any 2 stakeholders?
Analyse:
  For the 2 Chosen evaluate their:
    Power – High/Low
    Interest – High/Low
Mapping:
  Post your Stakeholders identified onto the grid:
  https://padlet.com/andresamuel2005/stakeholder
Notes: HS2 tunnel protest will be first of many, says activist | Environmental activism | The Guardian

## Slide 51: Overall Project Risk

## Slide 52: Risks
Definitions
Individual Project Risk – “is an uncertain event or condition that, if it occurs, has a positive or negative effect on one or more project objectives.” PMI, 2021, pp. 248
Overall Project Risk – “is the effect of uncertainty on the project as a whole, arising from all sources of uncertainty including individual risks, representing the exposure of stakeholders to the implications of variations in project outcome, both positive and negative.” PMI, 2017, pp. 435
Risk & Uncertainty
Adaptivity & Resilience

## Slide 53: Sources of Risk: Internal
Maylor (2017, pp. 221) proposes these Key Project Risk Categories:
Health and safety
Legal
Also, you may want to consider: Resources
Scope
Cost
Time
Quality
Risk & Uncertainty
Adaptivity & Resilience

## Slide 54: External sources of risk: Stakeholders and PESTLE
Consider risks from Stakeholders
Consider Environmental Risks (PESTLE)
Political context, Consideration of influence upon Government policies, taxation changes, foreign trade regulations, political risk in foreign markets, changes in trade blocks (EU).
Economic context, Consideration of influence upon business cycles, interest rates, personal disposable income, exchange rates, unemployment rates, GDP trends.
Socio-cultural factor context, Consideration of influence upon population changes, income distribution, lifestyle changes, consumerism, changes in culture and fashion.
Risk & Uncertainty
Adaptivity & Resilience

## Slide 55: External sources of risk: PESTLE continued
Technological context, Consideration of influence upon new discoveries and technology developments, ICT innovations, rates of obsolescence, increased spending on R&D.
Environmental context, Consideration of influence upon environmental protection regulations, energy consumption, global warming, waste disposal and re-cycling.
Legal context, Consideration of influence upon competition laws, health and safety laws, employment laws, licensing laws, IPR laws.
Risk & Uncertainty
Adaptivity & Resilience

## Slide 56: Activity: Identifying Project Risk
Using:
  Ikea’s expansion into India
What are/were the main risks?
  Internal – cost, scope, quality and time, resources and legal
  External – stakeholders and PESTLE
Discuss in your Breakout Rooms.
Post 1 Internal Risk and 1 External Risk
https://padlet.com/andresamuel2005/idrisks

## Slide 57: Project Charter

## Slide 58: Purpose of the Project Charter
Bring together Project Start Up into one document for project governance
  Formal/informal
  its background
  the reasons why it is being carried out
  the choice of options available for the project approach and outcome (it is important to include a ‘do nothing’ option to aid effective decision making)
  the planned benefits the known risks
  costs
  the timescales envisaged
  Owned by Project sponsor – Maintained by Project Manager
Stewardship & Governance

## Slide 59: End Result: Project Charter (from PMI, 2017) also called a Project Initiation Document (PID)
Contents of a Project Charter:
Project Purpose
Measurable project objectives and related success criteria
High-level requirements
High-level project description, boundaries and key deliverables
Overall project risk
Summary milestone schedule
Preapproved financial resources
Key stakeholder list
Project approval requirements (what constitutes success, who decides the project is successful, who signs off o the project
Project exit criteria (i.e.. What are the conditions to be met In order to close or to cancel the project or phase)
Assigned project management, responsibility, and authority level
Name and authority of the sponsor or other person(s) authorising the project charter
What?
Purpose, objectives, requirements
Risks
Timing and Resources
Stakeholders
Approval and authority
Integrated Planning
Managing Deployment
Project Start Up
Project Close
Monitoring &
Controlling Processes

## Slide 60: Example
Different companies will have their own format for the document for you to follow
Integrated Planning
Managing Deployment
Project Start Up
Project Close
Monitoring &
Controlling Processes

## Slide 61: Example Project Charter (or PID), Restaurant example
Project Name | Delicious and Healthy
Project Sponsor | C. Rich
Date of Project Approval | 15 Jan
Project Description | To launch a new restaurant with a “Delicious and Healthy” theme, where customers feel they can go to relax and enjoy the food. Create a dining experience that takes away concerns about calorie intake, fat, excess sugar, salt, etc.
Scope and boundaries | “Delicious and Healthy” restaurant will need to be designed and implemented in terms of: menu; logo and branding and restaurant layout and feel. The customer service experience is out of scope as “Delicious and Healthy” customer service approach will mirror the parent company’s already defined processes. The recruitment of staff for the restaurant is outside of the project scope as this will be managed by the parent company. The kitchen layout and functionality is out of scope as this will be managed by the parent company.
Business Case | To diversify the parent company’s restaurant offering and increase sales, with a target of gaining return on investment in 2 years. To tap into a segment of the market that wants to have healthy options on the menu, but take this further to innovate and create nutrition and taste themed experience. Recent surveys indicate that 71% of diners say health should not be disregarded (Hospitality and Catering News, 2020) and that 68% try to eat healthy all or most of the time (Mintel, 2021)
Project Manager | Helen Benton
Last Revision Date | 15 Jan
Notes: https://www.hospitalityandcateringnews.com/2020/01/new-restaurant-report-what-uk-consumers-want-from-eating-out/

## Slide 62: Objectives and Deliverables
Project Objectives | Design a restaurant interior that conveys comfort and health by 18 June in line with a budget of £820,000 Purchase all required restaurant fixtures and fittings to begin construction and installation on 18 June, with a total budget of £1,270,000 Liase with parent group on kitchen installation and recruitment/training with a completion date of 30 July. Oversee the installation of the restaurant to a high standard with a completion date of 30 July. Conduct market research into the tastes and customer preferences in the area by 11 June. Develop recipes that are delicious and designed with good nutrition using the recommended daily nutritional values by 2 July Establish supplier relationships with key suppliers by 16 July Test recipes with customers and consider feedback by 23 July Final menu confirmed by 30 July Develop marketing assets: logo, branding, tagline and visuals by 2 July Prepare and market launch event by 9 July Launch restaurant on 6th August
Project Deliverables and milestones | Restaurant facility ready for launch in August with a healthy and comfortable layout and feel ready for 30 July Menu designed and tested, ready for 30 July Supply chain and key relationships established ready for 30 JUly Marketing assets developed by July Launch event organised for August

## Slide 63: People, Stakeholders and Risks
Steering Committee | CEO Group Hospitality Director Group HR Director
Key Stakeholders | Project Sponsor: C Rich Project Team Contractors Consultants Existing restaurant franchises in the group
Key Risks | Procurement delays impacting the installation schedule Difficulties finding suppliers for key products Unable to develop food that is both healthy and delicious Customers do not like the menu etc
Project Team | Interior Designing Consultant Marketing Consultant Marketing intern Procurement Administrator Project Administrator Building contractor Electrical contractor Heating contractor
Competitors
Health and safety
Food standards agency
Local council
Customers

## Slide 64: It doesn’t end there!
Scope and requirements can change as the project progresses
Stakeholder Management and Engagement continues in the project lifecycle.
Risks need to be analysed and managed through the project lifecycle

## Slide 65: Summary of Start Up
Project Start Up is focused on determining what the project is about (and what it is not about)
Should include SMART (specific, measurable, activity, achievable, realistic and timely) Project Objectives.
Project Start Up has a focus on scope management by setting objectives and identifying the project requirements.
Stakeholders need to be managed as they can impact and are impacted by the project.
The internal team project, core externals and rest of the world are the main stakeholder groups.
Power and interest of each stakeholder needs to be considered.
Project risks can arise from internal and external sources.
There is more to do than identify stakeholders and risks – risk management and stakeholder engagement continues throughout the project lifecycle.
A Project Charter or PID brings together: project objectives, scope and requirements with key stakeholders and risks

## Slide 66: 011 Individual Assignment
011 Assessment Details

## Slide 67: You will create a Project Charter for Individual Assessment Part 3
Application of Project Management: A Project Charter, Plan and Management Response for one project (50%) Select ONE of the following potential new projects. You may choose any that interests you – but JUST ONE:
Digital Media Campaign to launch "Haklo Free", Project Sponsor is the Marketing Director (Business, Marketing focus)
Finance and Cost Auditing Project, Project Sponsor is the Finance Director (Business, Economics, Finance focus)
"Haklo Free" Launch Event, Project Sponsor is the Marketing Director (Business, Events, Tourism focus)
"Haklo Free" Design, Project Sponsor is the Design Director (Business, Events, Tourism focus)
Market Research for Potential Expansion of Haklo into a CIVETS country, Project Sponsor is the CEO (Business, Economics, Finance, International Business, Marketing, Tourism focus)
Recruitment Project for "Haklo Free" Team, Project Sponsor is the HR Director (Business and Human Resource focus)
Well-being Project, Project Sponsor is the HR Director (Business and Human Resource focus)
***FREE CHOICE OR MINI PROJECT OPTION*** - A project of your choice, this does not need to be focused on Haklo [Discuss with tutor to ensure your idea is viable and will meet the requirements of the assignment] ***FREE CHOICE OR MINI PROJECT OPTION***

## Slide 68
(a) Write a Project Charter for the Initiation of the Project (20%) Approx. 800 words [learning outcomes: LO1; LO2] Contents:
  Scope, goal and objectives of the project
  Stakeholder Analysis and Communication Approach
  Risk Analysis
  You will need to use the Project Charter Template

## Slide 69: Self-managed Study
Read Chapter 4 of Maylor (Kortext)
Have a go at the practice quiz
Continue working on your Part 1 - Reflection on Your Project Management Knowledge and Skills (15%)

## Slide 70: References
Association for Project Management, 2020. APM Body of Knowledge, 7th ed. Princes Risborough: Association for Project Management
Axelos Prince2, 2017. Managing Successful Projects with PRINCE2® 6th ed, London: TSO (The Stationery Office)
BBC News, 2016. Demolition of Surrey 'hidden castle' almost complete, BBC [online] Available at: <https://www.bbc.co.uk/news/uk-england-surrey-36445848/> [Accessed 15 May 2021].
BBC News, 2021. M&S hits back at Aldi's Cuthbert the Caterpillar cake revival, BBC [online] Available at: <https://www.bbc.co.uk/news/business-56812445/> [Accessed 15 May 2021].
Maylor, H. 2017. Project Management 4th ed. Harlow: Pearson Education
Maylor, H. 2017. Project Management 4th ed. Harlow: Pearson Education
Project Management Institute, 2017. A Guide to the Project Management Body of Knowledge, PMBOK Guide 6th ed. Newton Square, Pennsylvania: Project Management Institute Inc.
Project Management Institute, 2021. A Guide to the Project Management Body of Knowledge, PMBOK Guide 7th ed. Newton Square, Pennsylvania: Project Management Institute Inc.
Royce, W., 1970. Managing the Development of Large Software Systems, [online] Proceedings of IEEE WESCON, 26 (August): 1–9 Available at: < http://www-scf.usc.edu/~csci201/lectures/Lecture11/royce1970.pdf> [Accessed 3 May 2021].