## Slide 1
Guide to Using Project Libre
For Gantt Charts and Budget

## Slide 2: Steps to Build Gantt Chart
1. Complete dependency table with:
  Id
  Task name
  Duration
  Predecessor
2. Document your Assumptions:
  Holidays
  Start date
  etc

## Slide 3
3. Open Project Libre
  Click Create Project
  Enter Project Name
  Enter Project Start Date
  To set milestones:
    Create a milestone task name
    Set Duration to ‘0’ days
4. Enter Task name, Duration and Predecessor into rows

## Slide 4
5. Add holidays
  On FILE go to CALENDAR
  Select dates
  Set to NON-WORKING TIME
  Repeat for all holidays
6. Add Project Summary Task
  Insert New Task above task 1
    Right click on ID 1
    Choose New
    Type in Name of Project
  Select all Task below
  On TASK click INDENT

## Slide 5
7. Add Total Slack Column
  Right Click on Duration Column heading
  Choose Insert Column
  On Dialog box, choose Total Slack
8. Add Resources
  Go to RESOURCES click Resources Button
  Type in resource names
  Use separate rows for
  each resource
  Add the Standard Rates

## Slide 6
9. Assign Resources to Tasks
  Go back to Gantt Chart view
    TASK click Gantt
  Double click first task
  Go to Resources Tab
  Click Assign Button
  Select resource
  Click Assign
  Repeat for each Task
  Insert COST Column

## Slide 7
10. Add Overhead Cost Elements e.g. Accommodation
  Go to Gantt Chart View
  Add Cost Elements as a Task
  Enter project Duration
  Assign Resource to Task
  Repeat for each Overhead Cost
  element

## Slide 8
11. Add Fixed Cost to Gantt Chart
  Go back to Gantt Chart view
  Enter in new Row:
    Name- the Fixed Cost Elements e.g. Hardware
    Duration- ‘0’
  Insert Fixed Cost Column
  Enter the Amount in the Fixed Cost Column
  Repeat for each Fixed Cost element

## Slide 9
12. Screen Shots for Gantt Chart
  Before:
    Check that all the columns are visible
      Task, Cost, Total Slack, Duration, Start, Finish, Predecessor, Resources
    Check that all bars are visible
      On TASK
      Click Zoom Out
    Once, OK
    Use either Snipping Tool OR Prt Sc button on Keyboard
    Paste into Final Report

## Slide 10
13. Screen Shots for Budget
  Project Information Statistics Dialog Box
  Cost per Resource
    -> Go to Resource
    -> RBS
  Cost per Task
    -> Go to Task
    -> WBS