Case Study- Task 3.1 Gantt Chart and 3.2 Budget

Step 1: Initial Dependency Table

Using the details from in the case study pg. 12-15; Aruga Corporate Event Project information, Identify the tasks, durations, predecessors

Note: final adjustments to the estimated duration can be made later on when building Gantt Chart on Software, to meet time constraints and certain deadlines

| ID | Task Name | Duration (days) | Predecessor | Resources |
| --- | --- | --- | --- | --- |
| 1 | Jackson’s Corporate Dinner and Dance Setup Project |  |  |  |
| 2 | Sprint 1: Event scoping and requirements |  |  |  |
| 3 | Develop event theme and dress code options |  |  |  |
| 4 | Research available options for the entertainers and event production companies |  |  |  |
| 5 | Develop menu options |  |  |  |
| 6 | Develop layout and initial seating plan |  |  |  |
| 7 | Prepare for tasting menu and planning meeting |  |  |  |
| 8 | Tasting menu and planning meeting with Jackson’s |  |  |  |
| 9 | Agree on theme, entertainment, stage, menu and layout |  |  |  |
| 10 | Sprint 2: Communications and Guest management |  |  |  |
| 11 | Design and agree on invitations |  |  |  |
| 12 |  |  |  |  |
| …. |  |  |  |  |

Step 2: Document Assumptions:

- Number of workings days per week:

- Start Date:

- Project Deadline:

- Public Holidays:

- Budget Allocated:

- Cost Elements:

  - Direct Variable Costs-

  - Direct Fixed Costs-

  - Staffing Costs Rate-

Step 3: Build Gantt Chart in Project Libre

- Open Software, setup project with name and start date.

- Type in the Task Name, Duration and Predecessors

- Add Project Summary Task as the first task- this will show the total project duration

- Add Summary Task for each Sprint, indent the tasks below

- Add holidays based on assumptions, change working days etc

- Add column for Total Slack

Step 4- Check Project does not exceed deadline

If necessary:

- Change task durations

- Change task dependencies

Step 5- Assigned resources to each task

- Change Task Type to Fixed Duration

  - To be done task by task

  - Double click task name

  - Click advance tab

  - Change TYPE to Fixed Duration

- Add Resources and Rates in Resource Sheet

- Assign Resources to tasks,

  - one task at a time

  - Double click task name

  - Click Resources tab

  - Click Assign Resource button

  - You will need to work out the % for each resource

    - Assume work is shared equally among resources assigned to the task

    - Eg. Task duration is 5 days, Total Effort 10hrs (PM, A, SA-C)

      - 10hrs/80hrs = 12.5%/3 = 4% per person

- Insert Work Column- use this to check that the total effort is correct

  - If the work hrs displayed is not exact that total effort estimate, e.g. 9.6, and it should 10

  - Then type it in “10”, the software will prorate accordingly.

- Insert Cost Column, as you have already Assigned resources, the cost for each task would be populated

- Repeat for each Task

Step 6- Finalize Budget

- Add Variable and Fixed Cost

  - In the Gantt Chart view

  - Insert Fixed Cost Column

  - Enter in new Row/Task:

    - Name of the Variable/Fixed Cost Elements

    - Check that it is inline with the Sprints, if needed Outdent.

    - Set Duration- ‘0’

    - Set Predecessor

    - Enter the Amount in the Fixed Cost Column

        - Calculate for Variable Cost before entering

          - Eg. Menu= no of guest x rate

- Repeat for each Variable/Fixed Cost element

Step 7- Screenshot for Gantt Chart:

- Go to Gantt View

- Print Screen/Screen Shot

- Paste into Part 3.1 Body of the Final Report

Ensure that all columns are included and the bars (use Zoom Out)

Use Multiple Screenshots if necessary

Step 8- Screenshot for Budget:

- Project Information Statistics Dialog Box

- File -> Information -> Statistics

- Cost per Resource

  - Go to Resource-> RBS

- Cost per Sprint

  - Go to Task-> WBS

  - Make sure to roll up each Sprint, so only the cost for each Sprint will show up and the Variable/Fixed Cost Items

- Paste All the above screenshots into Part 3.2 of Final Report

Make sure these screenshots are visible, readable!

Step 9- Write up explanations for both Part 3.1 and 3.2 in Final Report

- See 011 Guidelines